Direct Outreach to Trafford Council and Local Schools

CassAI Community Learning Pilot – Trafford

Purpose

The CassAI pilot will begin direct outreach to local decision-makers within Trafford Council and nearby schools to identify a partner organisation willing to host the initial pilot.

Rather than relying solely on remote communication, the proposal will be introduced in person, allowing stakeholders to ask questions and review the pilot materials directly.

The goal is to secure one host partner for the first pilot phase.

Target Organisations

Initial outreach will focus on:

Trafford Council

Relevant departments may include:

- education services

- digital inclusion programmes

- community development teams

Local Schools

The proposal will be introduced to several schools within the Trafford area, particularly those that:

- support learners with additional needs

- run digital learning initiatives

- have interest in new learning technologies

Community Learning Organisations

Additional partners may include:

- youth centres

- community learning hubs

- charities supporting young people or adult learners

Proposal Introduction

When meeting potential partners, the CassAI pilot will be introduced with a short explanation of the project.

The key points include:

• a locally developed AI-supported learning pilot
• shared-device access to learning tools
• focus on learners who benefit from additional support
• a short pilot period designed to test real-world use

The proposal will include a one-page pilot overview outlining the scope, safety measures, and success target.

Pilot Request

Partners will be asked whether they would be interested in hosting a small pilot.

The pilot request includes:

- providing a supervised space for shared devices

- allowing learners to access the system during the pilot period

- helping evaluate the usefulness of the learning tools

Participation can be supported through either:

• a small pilot service fee to support operations
• in-kind support such as providing space or supervision

Pilot Outcome Measurement

The pilot will measure one simple outcome:

100 unique device accesses during the pilot period.

A short report summarising results and lessons learned will be shared with the partner organisation after the pilot concludes.

Follow-Up

If a partner expresses interest, the next steps will include:

- scheduling a short meeting to discuss pilot setup

- confirming the pilot location

- agreeing the pilot timeline and participation terms