Soft-Launch Readiness Checklist

CassAI Community Learning Pilot – Trafford

Before running pilot sessions, the CassAI system completes a short readiness check covering site setup, technology, and support procedures.

1. Pilot Site, Power, and Network

The pilot requires a safe and stable location where shared devices can be used.

Requirements include:

• supervised learning environment
• reliable electricity supply
• stable local network connection where available
• safe storage for devices when not in use

Possible pilot sites include:

• participating schools
• community learning hubs
• local partner organisations

These environments allow learners to access the system safely under supervision.

2. Local AI System Installed (Offline-First)

The CassAI learning system is designed to operate using local artificial intelligence models running on available hardware, allowing the service to function even when internet access is limited.

Before pilot sessions begin:

• local model runtime is installed
• offline inference is tested
• guardrails and safety filters are verified
• basic performance checks are completed

This ensures the system can provide reliable responses during pilot sessions.

3. Consent, Data and Safeguarding Forms

Before using the system, participants must review and accept the pilot consent notice.

Documents prepared include:

• participant consent notice
• privacy notice
• safeguarding guidelines
• equipment use rules

For minors, participation takes place under school or partner supervision.

These documents ensure the pilot follows basic data protection and safeguarding practices.

4. Helper Training and Support Flow

Teachers, volunteers, or community mentors supporting the pilot will receive a short orientation covering:

• how learners start a session
• how to assist with basic technical issues
• how to record session activity
• how to log device sign-out and returns

This ensures learners receive help if needed while keeping the system simple and accessible.

5. Device Access Tracker

A simple tracking system will monitor progress toward the pilot target.

The tracker records:

• number of unique device users
• number of sessions
• device locations
• progress toward the pilot target

The pilot success signal remains:

100 unique device accesses during the pilot period

Tracking may be done through a simple dashboard or log sheet.